## Light
PROJECT:
Training a Model on Moral Dilemmas: How AI ‘Thinks’ About Ethics.
Lee Ling Jun
| Project start date: | 2025-09-21 |  |  |  |  | Legend: |  |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
| Scrolling increment: | 0 |  |  | 2025-10-29
[10 empty] | September | [22 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [22 empty] | August
 | time axis 2025-09-21 to 2026-08-11
| Milestone description | Milestones \ Goals | Priority | Assigned to | Progress | Start | Days | Working Days | Days to Deadline | time axis 2025-09-21 to 2026-08-11
1 | 1. Project Scoping & Background Research |  |  |  |  | 2025-09-21
| Finalize research questions, scope, and hypotheses |  | Complete | Name | 100% | 2025-09-21 | 10 | 8 | -28
| Conduct literature review on AI + morality, datasets, interpretability, Chinese Room, Models selection |  | High risk |  | 50% | 2025-10-01 | 15 | 12 | -13
| Literature review on model selection |  | High risk |  | 10% | 2025-10-16 | 15 | 12 | 2
| Define evaluation metrics and success criteria |  | Complete |  | 100% | 2025-10-31 | 8 | 6 | 10
2. Dataset Design & Collection
| Choose dataset focus (cross-cultural, uncertainty, etc.) |  | Complete |  | 100% | 2025-11-08 | 14 | 10 | 24
| Combining Dataset |  | High risk |  | 0% | 2025-11-22 | 7 | 5 | 31
| Cleaning up Data set |  | High risk |  | 0% | 2025-11-29 | 5 | 4 | 36
| Preliminary data set exploration |  | High risk |  | 0% | 2025-12-04 | 5 | 4 | 41
3. Model Selection & Setup
| Choose baseline models (rule-based, shallow) |  | High risk |  | 0% | 2025-12-09 | 5 | 4 | 46
| Choose transformer models (LLaMA, GPT, Mistral, etc.) |  | Medium risk |  | 0% | 2025-12-14 | 7 | 5 | 53
| Set up training environment (Python, GPUs, libraries) |  | On track |  | 0% | 2025-12-21 | 37 | 27 | 90
4. Training & Fine-tuning
| Preprocess dataset and tokenization |  | On track |  | 0% | 2026-01-27 | 10 | 9 | 100
| Fine-tune baseline models on ETHICS |  | On track |  | 0% | 2026-02-06 | 12 | 9 | 112
| Fine-tune models on your custom dataset |  | On track |  | 0% | 2026-02-18 | 14 | 11 | 126
| Sanity-check and validate model outputs |  | On track |  | 0% | 2026-03-04 | 7 | 6 | 133
5. Evaluation
| Define and calculate evaluation metrics (accuracy, robustness, bias) |  | On track |  | 0% | 2026-03-11 | 2 | 3 | 135
| Conduct interpretability analysis (attention, embeddings, interventions) |  | On track |  | 0% | 2026-03-13 | 14 | 11 | 149
| Cross-cultural or moral uncertainty tests |  | On track |  | 0% | 2026-03-27 | 15 | 11 | 164
6. Analysis & Reflection
| Relate findings to philosophical framing (Chinese Room, etc.) |  | On track |  | 0% | 2026-04-11 | 9 | 6 | 173
| Identify limitations, biases, implications |  | On track |  | 0% | 2026-04-20 | 7 | 6 | 180
7. Write-up & Presentation
| Draft report/paper (intro, method, results) |  | On track |  | 0% | 2026-04-27 | 18 | 15 | 198
| Create figures, charts (attention maps, embeddings, Gantt chart) |  | On track |  | 0% | 2026-05-15 | 15 | 11 | 213
| Revise, finalize, and prepare presentation |  | On track |  | 0% | 2026-05-30 | 14 | 10 | 227
8. Deadlines
| Project and Data Management | Goal |  |  | 0% | 2025-10-30 | 1 | 2 | 2 | 2025-10-30: 2
| ViVa | Goal |  |  | 0% | 2026-06-30 | 1 | 2 | 245 | 2026-06-30: 2
To add more data, Insert new rows ABOVE this one