## ProjectTaskList
Training a Model on Moral Dilemmas: How AI ‘Thinks’ About Ethics.
Lee Ling Jun | [11 empty] | {42}
2025-09-21
PROJECT | TASK | Priority | START | PLAN END | ACTUAL END | Completion status(%) |  |  | Project Start | Days to Start | Complete | Incomplete | Slippage | Days | Working days
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | Done | 2025-09-21 | 2025-10-04 |  | 100% | 100 | 0 | 2025-09-21 | 0 | 10 | 0 | 0 | 13 | 10
| Conduct literature review on AI + morality, datasets | 2 | 2025-09-28 | 2025-10-19 |  | 50% | 50 | 50 | 2025-09-21 | 7 | 7.5 | 7.5 | 0 | 21 | 15
| Literature review on model selection | 1 | 2025-09-28 | 2025-10-19 |  | 10% | 10 | 90 | 2025-09-21 | 7 | 1.5 | 13.5 | 0 | 21 | 15
| Define evaluation metrics and success criteria | Done | 2025-10-14 | 2025-10-24 |  | 100% | 100 | 0 | 2025-09-21 | 23 | 8 | 0 | 0 | 10 | 8
2. Dataset Design & Collection | Choose dataset focus | Done | 2025-10-10 | 2025-10-30 |  | 100% | 100 | 0 | 2025-09-21 | 19 | 14 | 0 | 0 | 20 | 14
| Combining Dataset | 1 | 2025-10-29 | 2025-10-31 |  | 0% | 0 | 100 | 2025-09-21 | 38 | 0 | 2 | 0 | 2 | 2
| Cleaning up Data set | 4 | 2025-10-31 | 2025-11-16 |  | 0% | 0 | 100 | 2025-09-21 | 40 | 0 | 10 | 0 | 16 | 10
| Preliminary data set exploration | 4 | 2025-11-16 | 2025-11-23 |  | 0% | 0 | 100 | 2025-09-21 | 56 | 0 | 5 | 0 | 7 | 5
3. Model Selection & Setup | Choose baseline models | 4 | 2025-11-23 | 2025-11-27 |  | 0% | 0 | 100 | 2025-09-21 | 63 | 0 | 4 | 0 | 4 | 4
| Choose transformer models | 5 | 2025-11-27 | 2025-12-08 |  | 0% | 0 | 100 | 2025-09-21 | 67 | 0 | 7 | 0 | 11 | 7
| Set up training environment (Python, GPUs, libraries) | 5 | 2025-12-03 | 2025-12-04 |  | 0% | 0 | 100 | 2025-09-21 | 73 | 0 | 1 | 0 | 1 | 1
4. Training & Fine-tuning | Model Training | 5 | 2025-12-04 | 2026-01-22 |  | 0% | 0 | 100 | 2025-09-21 | 74 | 0 | 35 | 0 | 49 | 35
| Fine-tune models on your custom dataset | 5 | 2026-01-22 | 2026-03-16 |  | 0% | 0 | 100 | 2025-09-21 | 123 | 0 | 37 | 0 | 53 | 37
| Sanity-check and validate model outputs | 5 | 2026-03-11 | 2026-03-20 |  | 0% | 0 | 100 | 2025-09-21 | 171 | 0 | 7 | 0 | 9 | 7
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | 5 | 2026-03-20 | 2026-03-24 |  | 0% | 0 | 100 | 2025-09-21 | 180 | 0 | 2 | 0 | 4 | 2
| Conduct interpretability analysis (attention, embeddings, interventions) | 5 | 2026-03-24 | 2026-04-13 |  | 0% | 0 | 100 | 2025-09-21 | 184 | 0 | 14 | 0 | 20 | 14
| Cross-cultural or moral uncertainty tests | 5 | 2026-03-29 | 2026-04-18 |  | 0% | 0 | 100 | 2025-09-21 | 189 | 0 | 15 | 0 | 20 | 15
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | 5 | 2026-04-13 | 2026-04-24 |  | 0% | 0 | 100 | 2025-09-21 | 204 | 0 | 9 | 0 | 11 | 9
| Identify limitations, biases, implications | 5 | 2026-04-20 | 2026-04-29 |  | 0% | 0 | 100 | 2025-09-21 | 211 | 0 | 7 | 0 | 9 | 7
7. Write-up & Presentation | Draft report/paper (intro, method, results) | 5 | 2026-04-03 | 2026-04-29 |  | 0% | 0 | 100 | 2025-09-21 | 194 | 0 | 18 | 0 | 26 | 18
| Create figures, charts (attention maps, embeddings, Gantt chart) | 5 | 2026-04-13 | 2026-05-04 |  | 0% | 0 | 100 | 2025-09-21 | 204 | 0 | 15 | 0 | 21 | 15
| Revise, finalize, and prepare presentation | 5 | 2026-04-29 | 2026-05-19 |  | 0% | 0 | 100 | 2025-09-21 | 220 | 0 | 14 | 0 | 20 | 14
8. Deadlines | Project and Data Management | 1 | 2025-10-29 | 2025-10-30 | 2025-10-30 | 0% | 0 | 100 | 2025-09-21 | 38 | 0 | 1 | 0 | 1 | 1
| ViVa | 5 | 2026-06-29 | 2026-06-30 | 2025-10-30 | 0% | 0 | 100 | 2025-09-21 | 281 | 0 | 1 | -243 | 1 | 1
[42]
Formulas:
Priority = IF([PLAN END]="","", IF(OR([Completion status(%)]=1,[Completion status(%)]=100%),"Done", 6 - MAX(1,MIN(5, 1+([PLAN END]-TODAY()<=30)+([PLAN END]-TODAY()<=14)+([PLAN END]-TODAY()<=7)+([PLAN END]-TODAY()<=3) -IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.8,2,IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.5,1,0)) )) ))
Priority = IF([PLAN END]="","", IF(OR([Completion status(%)]=1,[Completion status(%)]=100%),"Done", 6 - MAX(1,MIN(5, 1+([PLAN END]-TODAY()<=30)+([PLAN END]-TODAY()<=14)+([PLAN END]-TODAY()<=7)+([PLAN END]-TODAY()<=3) -IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.8,2,IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.5,1,0)) )) ) )
Working days = IF(ISBLANK([PLAN END]), 0, SIGN([PLAN END]-[START]) * NETWORKDAYS( [START] + SIGN([PLAN END]-[START]), [PLAN END], H2:H49 ) )
Done – Task Complete (Green)
1 – Urgent (Red)
2 – High priority
3 – Medium priority
4 – Low priority
5 – Minimal urgency(light green)

## Gantt Chart (monthly view)
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gantt Chart (daily view)
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gantt Chart (weekly view)
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gantt Chart (monthly) fo report
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Sheet6
#NAME?
31
122
94

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/task-list-template.html
About
This task list template shows how you can create a gantt chart as a stacked bar chart in Excel. The Project Start date is the first series in the chart, but it is shown as a hidden bar by changing the fill color to None. The Minimum bound for the x-axis should be set to the Project Start date (and that is a manual process - see below).
Try a better approach to creating Gantt charts in Excel
Get Gantt Chart Template Pro for Excel
Adjust the Minimum Bound for the X-axis
When you change the Project Start date, you will need to also update the Minimum bound for the X-axis in the gantt chart. Right-click on the x-axis labels in the chart and go to Format Axis.
Adding More Rows
When you insert new rows, you should insert a blank row, then copy formulas down in the columns with the gray background.
Conditional Formatting
The Priority column uses conditional formatting to highlight cells differently based on their text value. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## Sheet2
Phase | Task | Start Date | End Date | Estimated Duration (weeks) | Estimated Duration (days roudup) | Notes / Deliverables
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | Sep 2, 2025 | Sep 15, 2025 | 2 | 14 | Define central problem and framing (AI & ethics).
| Conduct literature review on AI + morality, datasets, interpretability, Chinese Room | Sep 9, 2025 | Sep 30, 2025 | 3 | 21 | Build annotated bibliography.
| Define evaluation metrics and success criteria | Sep 25, 2025 | Oct 5, 2025 | 1.5 | 11 | Draft methodology outline.
2. Dataset Design & Collection | Choose dataset focus (cross-cultural, uncertainty, etc.) | Oct 1, 2025 | Oct 10, 2025 | 1.5 | 11 | Finalize dataset concept.
| Collect ethical dilemmas (texts, surveys, cultural sources) | Oct 10, 2025 | Nov 10, 2025 | 4 | 28 | Gather raw moral dilemmas.
| Design annotation schema and label guidelines | Oct 20, 2025 | Nov 5, 2025 | 2 | 14 | Define moral categories (fairness, duty, harm).
| Begin initial annotations / pilot study | Nov 5, 2025 | Nov 25, 2025 | 3 | 21 | Test consistency and reliability.
3. Model Selection & Setup | Choose baseline models (rule-based, shallow) | Dec 1, 2025 | Dec 10, 2025 | 1.5 | 11 | Implement simple baselines.
| Choose transformer models (LLaMA, GPT, Mistral, etc.) | Dec 10, 2025 | Dec 20, 2025 | 1.5 | 11 | Secure access / compute.
| Set up training environment (Python, GPUs, libraries) | Dec 15, 2025 | Jan 5, 2026 | 3 | 21 | Verify reproducibility setup.
4. Training & Fine-tuning | Preprocess dataset and tokenization | Jan 5, 2026 | Jan 20, 2026 | 2 | 14 | Clean, split, and validate data.
| Fine-tune baseline models on ETHICS | Jan 20, 2026 | Feb 5, 2026 | 2 | 14 | Establish baseline performance.
| Fine-tune models on your custom dataset | Feb 5, 2026 | Feb 25, 2026 | 3 | 21 | Train, log, and verify convergence.
| Sanity-check and validate model outputs | Feb 20, 2026 | Feb 29, 2026 | 1.5 | 11 | Qualitative inspection of reasoning.
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | Mar 1, 2026 | Mar 10, 2026 | 1.5 | 11 | Build evaluation scripts.
| Conduct interpretability analysis (attention, embeddings, interventions) | Mar 5, 2026 | Mar 25, 2026 | 3 | 21 | Visualize model reasoning patterns.
| Cross-cultural or moral uncertainty tests | Mar 10, 2026 | Mar 30, 2026 | 3 | 21 | Compare across groups or dilemmas.
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | Mar 25, 2026 | Apr 5, 2026 | 1.5 | 11 | Integrate technical + ethical insights.
| Identify limitations, biases, implications | Apr 1, 2026 | Apr 10, 2026 | 1.5 | 11 | Draft discussion section.
7. Write-up & Presentation | Draft report/paper (intro, method, results) | Mar 15, 2026 | Apr 10, 2026 | 3.5 | 25 | Prepare initial manuscript.
| Create figures, charts (attention maps, embeddings, Gantt chart) | Mar 25, 2026 | Apr 15, 2026 | 3 | 21 | Include in appendix or slides.
| Revise, finalize, and prepare presentation | Apr 10, 2026 | Apr 30, 2026 | 3 | 21 | Final thesis/presentation submission.

## Sheet3
Phase | Task | Start Date | End Date | Estimated Duration (days) | Notes / Deliverables
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | 2025-09-02 | 2025-09-15 | 14 | Define central problem and framing (AI & ethics). | 2025-09-21 | 2025-10-04
| Conduct literature review on AI + morality, datasets, interpretability, Chinese Room | 2025-09-09 | 2025-09-30 | 21 | Build annotated bibliography. | 2025-09-28 | 2025-10-19
| Define evaluation metrics and success criteria | 2025-09-25 | 2025-10-05 | 10 | Draft methodology outline. | 2025-10-14 | 2025-10-24
2. Dataset Design & Collection | Choose dataset focus (cross-cultural, uncertainty, etc.) | 2025-10-01 | 2025-10-10 | 10 | Finalize dataset concept. | 2025-10-20 | 2025-10-29
| Collect ethical dilemmas (texts, surveys, cultural sources) | 2025-10-10 | 2025-11-10 | 32 | Gather raw moral dilemmas. | 2025-10-29 | 2025-11-29
| Design annotation schema and label guidelines | 2025-10-20 | 2025-11-05 | 17 | Define moral categories (fairness, duty, harm). | 2025-11-08 | 2025-11-24
| Begin initial annotations / pilot study | 2025-11-05 | 2025-11-25 | 20 | Test consistency and reliability. | 2025-11-24 | 2025-12-14
3. Model Selection & Setup | Choose baseline models (rule-based, shallow) | 2025-12-01 | 2025-12-10 | 10 | Implement simple baselines. | 2025-12-20 | 2025-12-29
| Choose transformer models (LLaMA, GPT, Mistral, etc.) | 2025-12-10 | 2025-12-20 | 10 | Secure access / compute. | 2025-12-29 | 2026-01-08
| Set up training environment (Python, GPUs, libraries) | 2025-12-15 | 2026-01-05 | 22 | Verify reproducibility setup. | 2026-01-03 | 2026-01-24
4. Training & Fine-tuning | Preprocess dataset and tokenization | 2026-01-05 | 2026-01-20 | 15 | Clean, split, and validate data. | 2026-01-24 | 2026-02-08
| Fine-tune baseline models on ETHICS | 2026-01-20 | 2026-02-05 | 17 | Establish baseline performance. | 2026-02-08 | 2026-02-24
| Fine-tune models on your custom dataset | 2026-02-05 | 2026-02-25 | 21 | Train, log, and verify convergence. | 2026-02-24 | 2026-03-16
| Sanity-check and validate model outputs | 2026-02-20 | 2026-03-01 | 10 | Qualitative inspection of reasoning. | 2026-03-11 | 2026-03-20
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | 2026-03-01 | 2026-03-01 | 10 | Build evaluation scripts. | 2026-03-20 | 2026-03-20
| Conduct interpretability analysis (attention, embeddings, interventions) | 2026-03-05 | 2026-03-25 | 21 | Visualize model reasoning patterns. | 2026-03-24 | 2026-04-13
| Cross-cultural or moral uncertainty tests | 2026-03-10 | 2026-03-30 | 21 | Compare across groups or dilemmas. | 2026-03-29 | 2026-04-18
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | 2026-03-25 | 2026-04-05 | 12 | Integrate technical + ethical insights. | 2026-04-13 | 2026-04-24
| Identify limitations, biases, implications | 2026-04-01 | 2026-04-10 | 10 | Draft discussion section. | 2026-04-20 | 2026-04-29
7. Write-up & Presentation | Draft report/paper (intro, method, results) | 2026-03-15 | 2026-04-10 | 27 | Prepare initial manuscript. | 2026-04-03 | 2026-04-29
| Create figures, charts (attention maps, embeddings, Gantt chart) | 2026-03-25 | 2026-04-15 | 22 | Include in appendix or slides. | 2026-04-13 | 2026-05-04
| Revise, finalize, and prepare presentation | 2026-04-10 | 2026-04-30 | 21 | Final thesis/presentation submission. | 2026-04-29 | 2026-05-19

## Sheet4
PROJECT | TASK | Priority | START | PLAN END | ACTUAL END | Completion status(%) |  |  | Project Start | Days to Start | Complete | Incomplete | Slippage | Working days
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | Done | 2025-09-21 | 2025-10-04 |  | 100% | 100 | 0 | 2025-09-21 | 0 | 10 | 0 | 0 | 10
| Conduct literature review on AI + morality, datasets | 2 | 2025-09-28 | 2025-10-19 |  | 50% | 50 | 50 | 2025-09-21 | 7 | 7.5 | 7.5 | 0 | 15
| Literature review on model selection | 1 | 2025-09-28 | 2025-10-19 |  | 10% | 10 | 90 | 2025-09-21 | 7 | 1.5 | 13.5 | 0 | 15
| Define evaluation metrics and success criteria | Done | 2025-10-14 | 2025-10-24 |  | 100% | 100 | 0 | 2025-09-21 | 23 | 8 | 0 | 0 | 8
2. Dataset Design & Collection | Choose dataset focus (cross-cultural, uncertainty, etc.) | Done | 2025-10-10 | 2025-10-30 |  | 100% | 100 | 0 | 2025-09-21 | 19 | 14 | 0 | 0 | 14
| Combining Dataset | 3 | 2025-10-29 | 2025-11-09 |  | 0% | 0 | 100 | 2025-09-21 | 38 | 0 | 7 | 0 | 7
| Cleaning up Data set | 4 | 2025-11-09 | 2025-11-16 |  | 0% | 0 | 100 | 2025-09-21 | 49 | 0 | 5 | 0 | 5
| Preliminary data set exploration | 4 | 2025-11-16 | 2025-11-23 |  | 0% | 0 | 100 | 2025-09-21 | 56 | 0 | 5 | 0 | 5
3. Model Selection & Setup | Choose baseline models (rule-based, shallow) | 4 | 2025-11-20 | 2025-11-27 |  | 0% | 0 | 100 | 2025-09-21 | 60 | 0 | 5 | 0 | 5
| Choose transformer models (LLaMA, GPT, Mistral, etc.) | 5 | 2025-11-27 | 2025-12-08 |  | 0% | 0 | 100 | 2025-09-21 | 67 | 0 | 7 | 0 | 7
| Set up training environment (Python, GPUs, libraries) | 5 | 2025-12-03 | 2026-01-24 |  | 0% | 0 | 100 | 2025-09-21 | 73 | 0 | 37 | 0 | 37
4. Training & Fine-tuning | Preprocess dataset and tokenization | 5 | 2026-01-24 | 2026-02-08 |  | 0% | 0 | 100 | 2025-09-21 | 125 | 0 | 10 | 0 | 10
| Fine-tune baseline models on ETHICS | 5 | 2026-02-08 | 2026-02-24 |  | 0% | 0 | 100 | 2025-09-21 | 140 | 0 | 12 | 0 | 12
| Fine-tune models on your custom dataset | 5 | 2026-02-24 | 2026-03-16 |  | 0% | 0 | 100 | 2025-09-21 | 156 | 0 | 14 | 0 | 14
| Sanity-check and validate model outputs | 5 | 2026-03-11 | 2026-03-20 |  | 0% | 0 | 100 | 2025-09-21 | 171 | 0 | 7 | 0 | 7
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | 5 | 2026-03-20 | 2026-03-24 |  | 0% | 0 | 100 | 2025-09-21 | 180 | 0 | 2 | 0 | 2
| Conduct interpretability analysis (attention, embeddings, interventions) | 5 | 2026-03-24 | 2026-04-13 |  | 0% | 0 | 100 | 2025-09-21 | 184 | 0 | 14 | 0 | 14
| Cross-cultural or moral uncertainty tests | 5 | 2026-03-29 | 2026-04-18 |  | 0% | 0 | 100 | 2025-09-21 | 189 | 0 | 15 | 0 | 15
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | 5 | 2026-04-13 | 2026-04-24 |  | 0% | 0 | 100 | 2025-09-21 | 204 | 0 | 9 | 0 | 9
| Identify limitations, biases, implications | 5 | 2026-04-20 | 2026-04-29 |  | 0% | 0 | 100 | 2025-09-21 | 211 | 0 | 7 | 0 | 7
7. Write-up & Presentation | Draft report/paper (intro, method, results) | 5 | 2026-04-03 | 2026-04-29 |  | 0% | 0 | 100 | 2025-09-21 | 194 | 0 | 18 | 0 | 18
| Create figures, charts (attention maps, embeddings, Gantt chart) | 5 | 2026-04-13 | 2026-05-04 |  | 0% | 0 | 100 | 2025-09-21 | 204 | 0 | 15 | 0 | 15
| Revise, finalize, and prepare presentation | 5 | 2026-04-29 | 2026-05-19 |  | 0% | 0 | 100 | 2025-09-21 | 220 | 0 | 14 | 0 | 14
8. Deadlines | Project and Data Management | 1 | 2025-10-29 | 2025-10-30 | 2025-10-30 | 0% | 0 | 100 | 2025-09-21 | 38 | 0 | 1 | 0 | 1
| ViVa | 5 | 2025-06-29 | 2026-06-30 | 2025-10-30 | 0% | 0 | 100 | 2025-09-21 | -84 | 0 | 262 | -139 | 262
Formulas:
Priority = IF([PLAN END]="","", IF(OR([Completion status(%)]=1,[Completion status(%)]=100%),"Done", 6 - MAX(1,MIN(5, 1+([PLAN END]-TODAY()<=30)+([PLAN END]-TODAY()<=14)+([PLAN END]-TODAY()<=7)+([PLAN END]-TODAY()<=3) -IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.8,2,IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.5,1,0)) )) ))
Priority = IF([PLAN END]="","", IF(OR([Completion status(%)]=1,[Completion status(%)]=100%),"Done", 6 - MAX(1,MIN(5, 1+([PLAN END]-TODAY()<=30)+([PLAN END]-TODAY()<=14)+([PLAN END]-TODAY()<=7)+([PLAN END]-TODAY()<=3) -IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.8,2,IF(IF([Completion status(%)]>1,[Completion status(%)]/100,[Completion status(%)])>=0.5,1,0)) )) ) )
Working days = IF(ISBLANK([PLAN END]), 0, SIGN([PLAN END]-[START]) * NETWORKDAYS( [START] + SIGN([PLAN END]-[START]), [PLAN END], H2:H50 ) )

## Sheet1
Criterion | ETHICS (Hendrycks et al., 2021) | CMoralEval (Zhang et al., 2024) | MoralBench (Ji et al., 2024) | Moral Integrity Corpus (MIC, Ziems et al., 2022)
GDPR Compliance | Text-only dataset with no personally identifiable information (PII). Dataset card explicitly notes “no personal or sensitive data”. 🔗 ETHICS HuggingFace Dataset Card | Data derived from Chinese media and public examples, manually paraphrased and anonymised. Paper confirms “no individual information or personal identifiers included.” 🔗 ACL Findings 2024 Paper (PDF) | All data synthetically generated by large language models; authors state “no personally identifiable information is included in any sample.” 🔗 arXiv 2406.04428v2 – MoralBench | Derived from open-domain chatbot prompts (e.g. BlenderBot, GPT-2) and crowd annotations, all anonymised. No human participant data or PII. Dataset statement confirms “contains no personally identifiable or sensitive data.” 🔗 MIC GitHub Repository
UH Ethical Policies | Secondary, anonymised data under MIT licence, publicly released for academic research—fits UH policy for secondary use of anonymised text. | Secondary text dataset (anonymised, non-human participant data). Openly available and derived from media content, aligns with UH research-ethics guidelines for secondary data. | Fully synthetic text, publicly available; no human participants. Aligns with UH’s definition of exempt anonymised secondary data. | Research-only dataset containing anonymised conversational text. Fits UH guidelines for secondary, publicly available data without human subject involvement.
Permission to Use | Released under the MIT License. Open for research and non-commercial use. 🔗 GitHub License File | Licensed under CC BY-SA 4.0. Attribution required, free for research and educational use. 🔗 GitHub – CMoralEval License | Licensed under CC BY 5.0 according to repository and paper. Publicly available via GitHub and arXiv. 🔗 MoralBench GitHub | Licensed under CC BY-SA 4.0. Clearly stated in the repository README and license file. 🔗 MIC GitHub License
Original Data Ethics | Created by researchers from UC Berkeley, Google Research, and UC San Diego. Paper documents ethical use of data and adherence to institutional standards. 🔗 ICLR 2021 Paper | Authored by Tianjin University NLP Lab; ACL publication peer-reviewed, includes ethical considerations section confirming responsible data use. 🔗 ACL 2024 Findings Paper | Developed by AGI Research Group; dataset is fully synthetic and does not use human-sourced private data. Paper provides ethics statement affirming no sensitive or personal data were included. 🔗 arXiv 2406.04428v2 | Developed by Georgia Institute of Technology and University of Washington. ACL 2022 peer-reviewed publication includes “Ethical Considerations” section confirming non-sensitive, anonymised data and ethical oversight. 🔗 ACL 2022 Paper