## Gantt Chart (daily view)
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gantt Chart (weekly view)
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gantt Chart (monthly view)
Estimated Duration (days roudup)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## ProjectTaskList
Training a Model on Moral Dilemmas: How AI ‘Thinks’ About Ethics.
Lee Ling Jun | [9 empty] | {42}
|  | Project Start | 2025-09-21
PROJECT | TASK | PRIORITY | START | PLAN END | ACTUAL END | % COMPLETE | Project Start | Days to Start | Complete | Incomplete | Slippage | Plan Days
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | LOW | 2025-09-21 | 2025-10-04 |  | 0% | 2025-09-21 | 0 | 0 | 13 | 0 | 13
| Conduct literature review on AI + morality, datasets, interpretability, Chinese Room | LOW | 2025-09-28 | 2025-10-19 |  | 0% | 2025-09-21 | 7 | 0 | 21 | 0 | 21
| Define evaluation metrics and success criteria | LOW | 2025-10-14 | 2025-10-24 |  | 0% | 2025-09-21 | 23 | 0 | 10 | 0 | 10
2. Dataset Design & Collection | Choose dataset focus (cross-cultural, uncertainty, etc.) | LOW | 2025-10-20 | 2025-10-29 |  | 0% | 2025-09-21 | 29 | 0 | 9 | 0 | 9
| Collect ethical dilemmas (texts, surveys, cultural sources) | LOW | 2025-10-29 | 2025-11-29 |  | 0% | 2025-09-21 | 38 | 0 | 31 | 0 | 31
| Design annotation schema and label guidelines | LOW | 2025-11-08 | 2025-11-24 |  | 0% | 2025-09-21 | 48 | 0 | 16 | 0 | 16
| Begin initial annotations / pilot study | LOW | 2025-11-24 | 2025-12-14 |  | 0% | 2025-09-21 | 64 | 0 | 20 | 0 | 20
3. Model Selection & Setup | Choose baseline models (rule-based, shallow) | LOW | 2025-12-20 | 2025-12-29 |  | 0% | 2025-09-21 | 90 | 0 | 9 | 0 | 9
| Choose transformer models (LLaMA, GPT, Mistral, etc.) | LOW | 2025-12-29 | 2026-01-08 |  | 0% | 2025-09-21 | 99 | 0 | 10 | 0 | 10
| Set up training environment (Python, GPUs, libraries) | LOW | 2026-01-03 | 2026-01-24 |  | 0% | 2025-09-21 | 104 | 0 | 21 | 0 | 21
4. Training & Fine-tuning | Preprocess dataset and tokenization | LOW | 2026-01-24 | 2026-02-08 |  | 0% | 2025-09-21 | 125 | 0 | 15 | 0 | 15
| Fine-tune baseline models on ETHICS | LOW | 2026-02-08 | 2026-02-24 |  | 0% | 2025-09-21 | 140 | 0 | 16 | 0 | 16
| Fine-tune models on your custom dataset | LOW | 2026-02-24 | 2026-03-16 |  | 0% | 2025-09-21 | 156 | 0 | 20 | 0 | 20
| Sanity-check and validate model outputs | LOW | 2026-03-11 | 2026-03-20 |  | 0% | 2025-09-21 | 171 | 0 | 9 | 0 | 9
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | LOW | 2026-03-20 | 2026-03-24 |  | 0% | 2025-09-21 | 180 | 0 | 4 | 0 | 4
| Conduct interpretability analysis (attention, embeddings, interventions) | LOW | 2026-03-24 | 2026-04-13 |  | 0% | 2025-09-21 | 184 | 0 | 20 | 0 | 20
| Cross-cultural or moral uncertainty tests | LOW | 2026-03-29 | 2026-04-18 |  | 0% | 2025-09-21 | 189 | 0 | 20 | 0 | 20
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | LOW | 2026-04-13 | 2026-04-24 |  | 0% | 2025-09-21 | 204 | 0 | 11 | 0 | 11
| Identify limitations, biases, implications | LOW | 2026-04-20 | 2026-04-29 |  | 0% | 2025-09-21 | 211 | 0 | 9 | 0 | 9
7. Write-up & Presentation | Draft report/paper (intro, method, results) | LOW | 2026-04-03 | 2026-04-29 |  | 0% | 2025-09-21 | 194 | 0 | 26 | 0 | 26
| Create figures, charts (attention maps, embeddings, Gantt chart) | LOW | 2026-04-13 | 2026-05-04 |  | 0% | 2025-09-21 | 204 | 0 | 21 | 0 | 21
| Revise, finalize, and prepare presentation | LOW | 2026-04-29 | 2026-05-19 |  | 0% | 2025-09-21 | 220 | 0 | 20 | 0 | 20
Insert new rows above this one
[42]

## Help
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/task-list-template.html
About
This task list template shows how you can create a gantt chart as a stacked bar chart in Excel. The Project Start date is the first series in the chart, but it is shown as a hidden bar by changing the fill color to None. The Minimum bound for the x-axis should be set to the Project Start date (and that is a manual process - see below).
Try a better approach to creating Gantt charts in Excel
Get Gantt Chart Template Pro for Excel
Adjust the Minimum Bound for the X-axis
When you change the Project Start date, you will need to also update the Minimum bound for the X-axis in the gantt chart. Right-click on the x-axis labels in the chart and go to Format Axis.
Adding More Rows
When you insert new rows, you should insert a blank row, then copy formulas down in the columns with the gray background.
Conditional Formatting
The Priority column uses conditional formatting to highlight cells differently based on their text value. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## Sheet2
Phase | Task | Start Date | End Date | Estimated Duration (weeks) | Estimated Duration (days roudup) | Notes / Deliverables
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | Sep 2, 2025 | Sep 15, 2025 | 2 | 14 | Define central problem and framing (AI & ethics).
| Conduct literature review on AI + morality, datasets, interpretability, Chinese Room | Sep 9, 2025 | Sep 30, 2025 | 3 | 21 | Build annotated bibliography.
| Define evaluation metrics and success criteria | Sep 25, 2025 | Oct 5, 2025 | 1.5 | 11 | Draft methodology outline.
2. Dataset Design & Collection | Choose dataset focus (cross-cultural, uncertainty, etc.) | Oct 1, 2025 | Oct 10, 2025 | 1.5 | 11 | Finalize dataset concept.
| Collect ethical dilemmas (texts, surveys, cultural sources) | Oct 10, 2025 | Nov 10, 2025 | 4 | 28 | Gather raw moral dilemmas.
| Design annotation schema and label guidelines | Oct 20, 2025 | Nov 5, 2025 | 2 | 14 | Define moral categories (fairness, duty, harm).
| Begin initial annotations / pilot study | Nov 5, 2025 | Nov 25, 2025 | 3 | 21 | Test consistency and reliability.
3. Model Selection & Setup | Choose baseline models (rule-based, shallow) | Dec 1, 2025 | Dec 10, 2025 | 1.5 | 11 | Implement simple baselines.
| Choose transformer models (LLaMA, GPT, Mistral, etc.) | Dec 10, 2025 | Dec 20, 2025 | 1.5 | 11 | Secure access / compute.
| Set up training environment (Python, GPUs, libraries) | Dec 15, 2025 | Jan 5, 2026 | 3 | 21 | Verify reproducibility setup.
4. Training & Fine-tuning | Preprocess dataset and tokenization | Jan 5, 2026 | Jan 20, 2026 | 2 | 14 | Clean, split, and validate data.
| Fine-tune baseline models on ETHICS | Jan 20, 2026 | Feb 5, 2026 | 2 | 14 | Establish baseline performance.
| Fine-tune models on your custom dataset | Feb 5, 2026 | Feb 25, 2026 | 3 | 21 | Train, log, and verify convergence.
| Sanity-check and validate model outputs | Feb 20, 2026 | Feb 29, 2026 | 1.5 | 11 | Qualitative inspection of reasoning.
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | Mar 1, 2026 | Mar 10, 2026 | 1.5 | 11 | Build evaluation scripts.
| Conduct interpretability analysis (attention, embeddings, interventions) | Mar 5, 2026 | Mar 25, 2026 | 3 | 21 | Visualize model reasoning patterns.
| Cross-cultural or moral uncertainty tests | Mar 10, 2026 | Mar 30, 2026 | 3 | 21 | Compare across groups or dilemmas.
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | Mar 25, 2026 | Apr 5, 2026 | 1.5 | 11 | Integrate technical + ethical insights.
| Identify limitations, biases, implications | Apr 1, 2026 | Apr 10, 2026 | 1.5 | 11 | Draft discussion section.
7. Write-up & Presentation | Draft report/paper (intro, method, results) | Mar 15, 2026 | Apr 10, 2026 | 3.5 | 25 | Prepare initial manuscript.
| Create figures, charts (attention maps, embeddings, Gantt chart) | Mar 25, 2026 | Apr 15, 2026 | 3 | 21 | Include in appendix or slides.
| Revise, finalize, and prepare presentation | Apr 10, 2026 | Apr 30, 2026 | 3 | 21 | Final thesis/presentation submission.

## Sheet3
Phase | Task | Start Date | End Date | Estimated Duration (days) | Notes / Deliverables
1. Project Scoping & Background Research | Finalize research questions, scope, and hypotheses | 2025-09-02 | 2025-09-15 | 14 | Define central problem and framing (AI & ethics). | 2025-09-21 | 2025-10-04
| Conduct literature review on AI + morality, datasets, interpretability, Chinese Room | 2025-09-09 | 2025-09-30 | 21 | Build annotated bibliography. | 2025-09-28 | 2025-10-19
| Define evaluation metrics and success criteria | 2025-09-25 | 2025-10-05 | 10 | Draft methodology outline. | 2025-10-14 | 2025-10-24
2. Dataset Design & Collection | Choose dataset focus (cross-cultural, uncertainty, etc.) | 2025-10-01 | 2025-10-10 | 10 | Finalize dataset concept. | 2025-10-20 | 2025-10-29
| Collect ethical dilemmas (texts, surveys, cultural sources) | 2025-10-10 | 2025-11-10 | 32 | Gather raw moral dilemmas. | 2025-10-29 | 2025-11-29
| Design annotation schema and label guidelines | 2025-10-20 | 2025-11-05 | 17 | Define moral categories (fairness, duty, harm). | 2025-11-08 | 2025-11-24
| Begin initial annotations / pilot study | 2025-11-05 | 2025-11-25 | 20 | Test consistency and reliability. | 2025-11-24 | 2025-12-14
3. Model Selection & Setup | Choose baseline models (rule-based, shallow) | 2025-12-01 | 2025-12-10 | 10 | Implement simple baselines. | 2025-12-20 | 2025-12-29
| Choose transformer models (LLaMA, GPT, Mistral, etc.) | 2025-12-10 | 2025-12-20 | 10 | Secure access / compute. | 2025-12-29 | 2026-01-08
| Set up training environment (Python, GPUs, libraries) | 2025-12-15 | 2026-01-05 | 22 | Verify reproducibility setup. | 2026-01-03 | 2026-01-24
4. Training & Fine-tuning | Preprocess dataset and tokenization | 2026-01-05 | 2026-01-20 | 15 | Clean, split, and validate data. | 2026-01-24 | 2026-02-08
| Fine-tune baseline models on ETHICS | 2026-01-20 | 2026-02-05 | 17 | Establish baseline performance. | 2026-02-08 | 2026-02-24
| Fine-tune models on your custom dataset | 2026-02-05 | 2026-02-25 | 21 | Train, log, and verify convergence. | 2026-02-24 | 2026-03-16
| Sanity-check and validate model outputs | 2026-02-20 | 2026-03-01 | 10 | Qualitative inspection of reasoning. | 2026-03-11 | 2026-03-20
5. Evaluation | Define and calculate evaluation metrics (accuracy, robustness, bias) | 2026-03-01 | 2026-03-01 | 10 | Build evaluation scripts. | 2026-03-20 | 2026-03-20
| Conduct interpretability analysis (attention, embeddings, interventions) | 2026-03-05 | 2026-03-25 | 21 | Visualize model reasoning patterns. | 2026-03-24 | 2026-04-13
| Cross-cultural or moral uncertainty tests | 2026-03-10 | 2026-03-30 | 21 | Compare across groups or dilemmas. | 2026-03-29 | 2026-04-18
6. Analysis & Reflection | Relate findings to philosophical framing (Chinese Room, etc.) | 2026-03-25 | 2026-04-05 | 12 | Integrate technical + ethical insights. | 2026-04-13 | 2026-04-24
| Identify limitations, biases, implications | 2026-04-01 | 2026-04-10 | 10 | Draft discussion section. | 2026-04-20 | 2026-04-29
7. Write-up & Presentation | Draft report/paper (intro, method, results) | 2026-03-15 | 2026-04-10 | 27 | Prepare initial manuscript. | 2026-04-03 | 2026-04-29
| Create figures, charts (attention maps, embeddings, Gantt chart) | 2026-03-25 | 2026-04-15 | 22 | Include in appendix or slides. | 2026-04-13 | 2026-05-04
| Revise, finalize, and prepare presentation | 2026-04-10 | 2026-04-30 | 21 | Final thesis/presentation submission. | 2026-04-29 | 2026-05-19

## Sheet4
Daily | weekly | monthly
2025-09-21 | 2025-09-21 | 2025-09-21
2025-09-22 | 2025-09-28 | 2025-10-21
2025-09-23 | 2025-10-05 | 2025-11-21
2025-09-24 | 2025-10-12 | 2025-12-21
2025-09-25 | 2025-10-19 | 2026-01-21
2025-09-26 | 2025-10-26 | 2026-02-21
2025-09-27 | 2025-11-02 | 2026-03-21
2025-09-28 | 2025-11-09 | 2026-04-21
2025-09-29 | 2025-11-16 | 2026-05-21
2025-09-30 | 2025-11-23 | 2026-06-21
2025-10-01 | 2025-11-30 | 2026-07-21
2025-10-02 | 2025-12-07 | 2026-08-21
2025-10-03 | 2025-12-14
2025-10-04 | 2025-12-21
2025-10-05 | 2025-12-28
2025-10-06 | 2026-01-04
2025-10-07 | 2026-01-11
2025-10-08 | 2026-01-18
2025-10-09 | 2026-01-25
2025-10-10 | 2026-02-01
2025-10-11 | 2026-02-08
2025-10-12 | 2026-02-15
2025-10-13 | 2026-02-22
2025-10-14 | 2026-03-01
2025-10-15 | 2026-03-08
2025-10-16 | 2026-03-15
2025-10-17 | 2026-03-22
2025-10-18 | 2026-03-29
2025-10-19 | 2026-04-05
2025-10-20 | 2026-04-12
2025-10-21 | 2026-04-19
2025-10-22 | 2026-04-26
2025-10-23 | 2026-05-03
2025-10-24 | 2026-05-10
2025-10-25 | 2026-05-17
2025-10-26 | 2026-05-24
2025-10-27 | 2026-05-31
2025-10-28 | 2026-06-07
2025-10-29 | 2026-06-14
2025-10-30 | 2026-06-21
2025-10-31 | 2026-06-28
2025-11-01 | 2026-07-05
2025-11-02 | 2026-07-12
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16
2026-01-17
2026-01-18
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-15
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-22
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
2026-03-01
2026-03-02
2026-03-03
2026-03-04
2026-03-05
2026-03-06
2026-03-07
2026-03-08
2026-03-09
2026-03-10
2026-03-11
2026-03-12
2026-03-13
2026-03-14
2026-03-15
2026-03-16
2026-03-17
2026-03-18
2026-03-19
2026-03-20
2026-03-21
2026-03-22
2026-03-23
2026-03-24
2026-03-25
2026-03-26
2026-03-27
2026-03-28
2026-03-29
2026-03-30
2026-03-31
2026-04-01
2026-04-02
2026-04-03
2026-04-04
2026-04-05
2026-04-06
2026-04-07
2026-04-08
2026-04-09
2026-04-10
2026-04-11
2026-04-12
2026-04-13
2026-04-14
2026-04-15
2026-04-16
2026-04-17
2026-04-18
2026-04-19
2026-04-20
2026-04-21
2026-04-22
2026-04-23
2026-04-24
2026-04-25
2026-04-26
2026-04-27
2026-04-28
2026-04-29
2026-04-30
2026-05-01
2026-05-02
2026-05-03
2026-05-04
2026-05-05
2026-05-06
2026-05-07
2026-05-08
2026-05-09
2026-05-10
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-17
2026-05-18
2026-05-19
2026-05-20
2026-05-21
2026-05-22
2026-05-23
2026-05-24
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2026-05-31
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-14
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20
2026-06-21
2026-06-22
2026-06-23
2026-06-24
2026-06-25
2026-06-26
2026-06-27
2026-06-28
2026-06-29
2026-06-30
2026-07-01
2026-07-02
2026-07-03
2026-07-04
2026-07-05
2026-07-06
2026-07-07
2026-07-08
2026-07-09
2026-07-10
2026-07-11
2026-07-12
2026-07-13
2026-07-14
2026-07-15
2026-07-16
2026-07-17
2026-07-18
2026-07-19
2026-07-20
2026-07-21
2026-07-22
2026-07-23
2026-07-24
2026-07-25
2026-07-26
2026-07-27
2026-07-28
2026-07-29
2026-07-30
2026-07-31